## Sheet1
Game | Bug | Programmer assigned | Start date of fixing | Time needed to fix | Actual Start Date | Actual End Date
Card Match | Tapping on background repeatedly after selecting second card will yield a nullreferenceexecption (easy) or missingcomponent (hard) | Jiaqing | 2014-05-30 | 1 Day | 2014-05-19 | 2014-05-19
| Returning to menu after completing hard will cause UI issues | Jiaqing | Not replicable | Not replicable
Operation Operator | The easy/hard level distinction is not obvious. For hard level, can consider solving the problem using at least 2 operators. | Jacky Question generation rewritten to support multilevel operations | 2014-06-02 | Est. 4 - 5 days | 2014/05/19
| Timer should be on per trial (response) basis | Jacky | 2014-06-02 | 1 Day | 2014-05-19
| Minor issue. Standardize the use of symbol ÷ and / ? | Jacky | 2014-06-02 | < 1 hr | 2014-05-19
| Remove the X on the clear button to avoid confusion with multiplication symbol or error? | Artists
| When player got it wrong, say [3+2] = 6 -> [5] = 6, the equal sign doesn’t feel right there? Or, it seems that player can keep going from there (wrong answer) to next level of operation say from [5] = 6 -> [5+1] = 6. The game seems to respond to additional levels of operation or trials [that also means no need to clear and start again for wrong answer]. Is that what it’s supposed to be (though not reflected in the instruction)? | Jacky | Nil - Yes, that is supposed to happen | Nil - Yes, that is supposed to happen
Shape Sorting | Realised that the answer is always the smallest number, for both easy and hard levels. Do randomize the answers | Darren | 2014-06-02 | 4 Days
| Some shapes have 5 triangles but no option to select 5 (See pic) confusion should be minimized | Artists
| Timer should be on per trial (response) basis | Darren | 2014-06-02 | 2 Days
| Of the 3 options of answers – if got it right the first time, a score of 10 point awarded. If got it wrong, player can also randomly guess and keep on clicking the next remaining 2 answers and if wrong again, only the correct answer left and the player can still get a full score of 10 point, just by randomly clicking or guesswork. Penalty can be built in to discourage guessing or mindless clicking. | Darren | 2014-06-02 | 1 Day
Number tapper | Timer need not include milliseconds | Darren | 2014-05-30 | 30 mins
| There might be a bug, score show 0 even with a number of correct trials | Darren | 2014-05-30 | 1 Day
| Instructions do not include tapping again to deselect a wrongly selected number. Games stops until you do so. | Instructions not clear - Artists
Cloud sort | Easy and hard modes might be switched. The easy level seems more difficult. | Darren | 2014-05-30 | 5 mins
| Sometimes, a star appears in the centre of the screen, preventing player from responding. | Darren | 2014-06-02 | Est. 2 Days
| A possibility that players may use strategy to always use small number for each operation in order to maximize the score – therefore, the score should also factor in number of trials | Darren | 2014-06-02 | 1 Day
+- Fruits | Just curious how the game got its name as game is not related to fruits. | Darren | 2014-05-31 | 4 Days
| Timer need not include milliseconds | Darren | 2014-05-30 | 30 mins
| To avoid ambiguity (cf. as mentioned above for mental math), X should be changed to “Clear” and √ to “Enter” | Artists
Mental Math | The sequence of number (~10) may be too long for a start. If player loses focus at the beginning, the entire trial is wasted just waiting for it to end. Is it feasible to have an option to end trial prematurely? | Jiaqing | 2014-06-02 | Est. 4 - 5 days
| There might be a bug, timer show 00s when the game is running (including at the point when ‘?’ appears and a response would have to be made) | Jiaqing | 2014-06-02 | 5 mins
| For the users. The symbol X could be confusing, does it mean wrong? Clear? Or multiply? For the symbol √, does it mean correct? Or does it mean enter? | Artists
What’s That shadow | If player got it wrong even for the first time, the game would just hang there and not proceed for new trials. There should be more than just one trial. The game should not stall and freeze there. No issue for player who got it right as the game would keep going. | Samuel | 2014-05-29 | 1 Day
Conveyor belt | Typo error in brief instructions. | Artists
| Game hangs when player completes one round. Android version 3.1 could be the cause of the problem | Jacky | 2014-06-04 | 1 Day | 2014-05-19 | 2014-05-19
| Instruction should be made clearer that the rule is “no remainder” | Artists
| The score didn’t do anything, only showing 0 all the time, even with correct responses, could be a bug | Jacky | 2014-06-04 | 1 Day | 2014-05-19 | 2014-05-19
| Minor issue: at the end of the game, a big red cross appeared (skewed to one side, aesthetically could improve the alignment) perhaps can use “Time’s up” instead of a cross – as it’s not an “error” and less demotivating – this could be a version issue. | Jacky | 2014-06-04 | 1 Day | 2014-05-19 | 2014-05-19
| Would Easy Mode be too fast for some, given the need to drag and drop? Long distance to drag into Etc. | Jacky | 2014-06-04 | 1 Day | 2014-05-19 | 2014-05-19
Dice game | May be difficult for player to understand game instruction. If trial is achievable, working memory is involved. | Artists
| When a trial gets too difficult, the player is heavily dependent on guesswork. | Samuel - Will fix in next update. Requires name and texture changes | 2014-06-02 | 1 Day
| Are the screens supposed to change color or is that a bug? | Probably Android Problem - Jacky will look into it | 2014-06-02 | 1 Day
Colour Sequencing | The target colour is perceived to be slightly different in colour, and this is probably due to the background colour. Consider having the same background colour. | Artists
| Screen changed color? | Probably Android Problem - Jacky will look into it | 2014-06-02 | 1 Day
| In some instances, the “score” was not doing anything, only 0 even with correct answers | Jacky | 2014-06-02 | 1 Day | 2014-05-19 | 2014-05-19
Fly Swatter | Pace a little slow. Can do away with introduction and summary for each trial. | Jiaqing | 2014-05-30 | 2 Days | 2014-05-20 | 2014-05-20
| Game should keep going instead of stopping at each short trial | Jiaqing | 2014-05-30 | 2 Days | 2014-05-20 | 2014-05-20
| Timer need not include milliseconds | Jiaqing | 2014-05-30 | < 1 hr | 2014-05-19 | 2014-05-19
| Flies that spawn outside of border spin for a while | Jiaqing |  |  | 2014-05-20 | 2014-05-20
| Flies overlap incorrectly | Jiaqing |  |  | 2014-05-20 | 2014-05-20